## Resource Availability
Local Expert Activites Resource Planning for 25 January to 07 February 2017
| Sprint Start Date | 2017-01-26
| Sprint End Date | 2017-02-07 | [5 empty] | Don’t change fields with this color
| Sprint Days | 9
| Holidays / Events | 1
| Available Sprint Days | 8
| Number of Engineers | 7
| Available Points | 82 | [9 empty] | 3.915
| Production Support ( % ) | 10
| On Call Consumes (%) | 75
| Effective Points | 73.8
Developer | Number of Leaves | On Call | Other Projects | Days Lost | Day Available | Points Available | Effective Points Available | Capacity Allocation in points
Ananth |  |  | 2 | 2 | 6 | 12 | 10.8 | 65% to Product Asks | 47.97 | Planned Programs 70% | 33.579
Girish | 1 |  |  | 1 | 7 | 14 | 12.6 |  |  | Opportunistic TnLs 30% | 14.391
Lokesh | 1 |  |  | 1 | 7 | 14 | 12.6 | 35% to Engineering Tasks | 25.83 | Pipeline Stability | 25.83
Prathik | 1 | 5 |  | 4.75 | 3.25 | 6.5 | 5.85 |  |  | Performance Optimization
Sharvani |  | 1 |  | 0.75 | 7.25 | 14.5 | 13.05 |  |  | Code Refactoring
Swathi |  |  | 2 | 2 | 6 | 12 | 10.8 |  |  | Upgrades
Vikas | 2 | 2 |  | 3.5 | 4.5 | 9 | 8.1 |  |  | Abacus Cleanup
[8 empty] | Production Support | 8.2 |  | 8.2

## Availability Calendar
| 2017-01-26 | 2017-01-27 | 2017-01-28 | 2017-01-29 | 2017-01-30 | 2017-01-31 | 2017-02-01 | 2017-02-02 | 2017-02-03 | 2017-02-04 | 2017-02-05 | 2017-02-06 | 2017-02-07
Ananth
Girish
Lokesh
Prathik
Sharvani
Swathi
Vikas
Holiday, Weekend or On Leave
Available
On Call

## Summary
Capacity Planning
Sprint Duration | 9 Days ( 12/Jan to 24/Jan)
Holidays | 0
Vacation Plan | 12 (Ananth 1, Prathik 1, Swathi, 1, Vikas 9)
# Developers | 5 (Girish, Lokesh, Prathik, Sharvani, Vikas)
# of Testers | 2 ( Swathi, Ananth)
Total Available Capacity | 82
Effective Capacity | 73.8

## Features List
Priority | ID | Title | Dev Owner | Test Owner | Dev Effort | Test Effort | Type of Work
1 | 3419 | Emmet: Fixing Errors of Fortify Scan - Classified as High | Lokesh |  | 2 |  | Support
1 | 3247 | [Itin] Revisit actual activity on complete your trips | Ananth | Ananth | 0 |  | Test and Learn
1 | 3221 | [Itin] Likely to sell out messaging | Prathik | Ananth | 6 |  | Test and Learn
1 | 2866 | Activities Near Current Location | Girish | Swathi | 4 |  | Test and Learn
1 | 3234 | Initiate Change-Search by clicking destination/date fields | Vikas | Swathi | 4 |  | Test and Learn
1 | 2965 | Default to Next Available Date for Dateless Traffic | Sharvani | Swathi | 8 |  | Test and Learn
1 | 2748 | Mobile Filter Interaction | Lokesh | Ananth | 4 |  | Test and Learn
1 | 3548 | MAIN- 162320 | Girish |  | 2 |  | Support
2 | 3451 | Fixing GMT Page Issues | Vikas |  | 8 |  | Support
2 | 3328 | LX Infosite Redesign | Sharvani | Swathi | 10 | 4 | Feature
2 | 3530 | DCTK Version Upgrade to 2.96 | Ananth |  | 3 |  | Support
3 | 3374 | UITK Upgrade to the latest version | Ananth |  | 3 |  | Support
3 | 3468 | Adding IDs for Automated tests | Swathi |  | 4 |  | Support
3 | 3454 | Perf Improvements: Preloading SRP Images | Girish | Ananth | 3 | 4 | Test and Learn
3 | 3375 | CSS Job with Abacus ON/OFF | Swathi |  | 2 |  | Engineering Feature
3 | 3274 | Timeouts setting based on environments | Ananth |  | 3 |  | Support
3 | 2553 | [Bug]Errors In Prod | Lokesh |  | 4 |  | Support
3 | 3540 | Bug with See More Results | Vikas |  | 3 |  | Support
Cut Line
4 | 3347 | Analysis: UITK Overrides |  |  | 4 |  | Engineering Feature
4 | 2819 | Tone of the Location Redirect Message |  |  | 4 |  | Test and Learn
4 | 2031 | Location - Redirect experience |  |  | 4 |  | Test and Learn
99 | 3531 | Testing HREF Lang Implementation |  |  | 99 |  | Engineering Feature
99 | 3467 | Integration of Shop with Supply Events |  |  | 99 |  | Engineering Feature
99 | 3373 | Bugs on VSC ITIN/POS7 Page |  |  | 99 |  | Rollout
99 | 3206 | Mobile SRP - Open Infosite in New Tab on Mobile |  |  | 99 |  | Test and Learn
99 | 3096 | [Hotel Address Anchored] Feature nearby activities |  |  | 99 |  | Test and Learn
Must Complete in the sprint Features
Priortized Features
Features not part of this sprint

## Sheet4
Priority | ID | Title | Dev Owner | Test Owner | Dev Effort | Test Effort | Type of Work
3 | 2553 | [Bug]Errors In Prod | Lokesh |  | 4 |  | Support
1 | 2748 | Mobile Filter Interaction | Lokesh | Ananth | 4 |  | Test and Learn
1 | 2866 | Activities Near Current Location | Girish | Swathi | 4 |  | Test and Learn
1 | 2965 | Default to Next Available Date for Dateless Traffic | Sharvani | Swathi | 8 |  | Test and Learn
1 | 3221 | [Itin] Likely to sell out messaging | Prathik | Ananth | 6 |  | Test and Learn
1 | 3234 | Initiate Change-Search by clicking destination/date fields | Vikas | Swathi | 4 |  | Test and Learn
1 | 3247 | [Itin] Revisit actual activity on complete your trips | Ananth | Ananth | 0 |  | Test and Learn
3 | 3274 | Timeouts setting based on environments | Ananth |  | 3 |  | Support
2 | 3328 | LX Infosite Redesign | Sharvani | Swathi | 10 | 4 | Feature
3 | 3374 | UITK Upgrade to the latest version | Ananth |  | 3 |  | Support
3 | 3375 | CSS Job with Abacus ON/OFF | Swathi |  | 2 |  | Engineering Feature
1 | 3419 | Emmet: Fixing Errors of Fortify Scan - Classified as High | Lokesh |  | 2 |  | Support
2 | 3451 | Fixing GMT Page Issues | Vikas |  | 8 |  | Support
3 | 3454 | Perf Improvements: Preloading SRP Images | Girish | Ananth | 3 | 4 | Test and Learn
3 | 3468 | Adding IDs for Automated tests | Swathi |  | 4 |  | Support
2 | 3530 | DCTK Version Upgrade to 2.96 | Ananth |  | 3 |  | Support
3 | 3540 | Bug with See More Results | Vikas |  | 3 |  | Support
1 | 3548 | MAIN- 162320 | Girish |  | 2 |  | Support

## Spill Overs
Priority | ID | Title | Dev Owner | Status | Planned Dev Points | Spilled Over Points
1 | 3381 | Automating E2E Tests | Ananth | Completed | 2 | 0
1 | 3467 | Integration of Shop with Supply Events | Girish | Completed | 8 | 0
1 | 3068 | Distance to Purchased Hotel | Lokesh | Completed | 4 | 0
1 | 2866 | Activities Near Current Location | Prathik | Completed | 4 | 0
1 | 3221 | [Itin] Likely to sell out messaging ( LX Web Side) | Prathik | Completed | 4 | 0
1 | 3465 | Allowing Ski Activities only in Package Path | Sharvani | Completed | 3 | 0 | Sprint # | Planned Points | Points Spilled Over | Points Burnt | Burn Rate
1 | 3328 | LX Infosite Redesign | Sharvani | Completed | 12 | 0 | 88 | 52 | 18 | 34 | 65.38%
1 | 2748 | Mobile Filter Interaction | Swathi | Completed | 0 | 0 | 89 | 50 | 3 | 47 | 94%
3 | 3421 | Analysis: Test Coverage of LX in EXPWEB | Swathi | Completed | 2 | 0 | 90 | 67 | 25 | 42 | 62.69%
3 | 3469 | Bug Bash Bug Triaging | Swathi | Completed | 1 | 0 | 91 | 66 | 26 | 40 | 60.61%
1 | 3247 | [Itin] Revisit actual activity on complete your trips | Ananth | Spill Over; Late identification of bugs | 0 | 1 | 92 | 60 | 20 | 40 | 66.67%
1 | 2866 | Activities Near Current Location | Girish | Spill Over; Production (sort) issue fix took time | 8 | 4 | 93 | 56 | 15 | 41 | 73.21%
1 | 2553 | [Bug]Errors In Prod | Sharvani | Spill Over; Was depriortised due to production issue | 4 | 4 | 94 | 60 | 32 | 28 | 46.67%
1 | 3375 | CSS Job with Abacus ON/OFF | Swathi | Spill Over; Took up the task last minute and pipeline wasn't ready to merge. | 2 | 3 | 95 | 77 | 30 | 47 | 61.04%
2 | 3374 | UITK Upgrade to 2.80 | Ananth | Spill Over; Took more time due to issues observed during upgrade | 4 | 3 | 96 | 76 | 38 | 38 | 50%
2 | 3419 | Emmet: Fixing Errors of Fortify Scan - Classified as High | Lokesh | Spill Over; Fortify Tool issues | 10 | 2 | 97 | 85 | 43 | 42 | 49.41%
2 | 3451 | Fixing GMT Page Issues | Prathik | Spill Over; Depriortised to take TnL | 8 | 8 | 98 | 93 | 30 | 63 | 67.74%
2 | 3468 | Analysis: Adding IDs for Automated tests | Swathi | Spill Over; Other tasks took time | 4 | 4 | 1 | 83 | 32 | 51 | 61.45%
4 | 3274 | Timeouts setting based on environments | Ananth | Spill Over; UTIK upgrade took time | 3 | 3

## Happiness Index
| Ananth | Girish | Lokesh | Prathik | Sharvani | Swathi | Vikas | Vijay | Ramesh | Average
Activities Shop Last | 6 | 6 | 6 | 6 | 7 | 7 |  | 8
Activities Sprint 1 | 6 | 6 | 5 | 6 |  | 7 |  | 7 | 6
Activities Sprint 2
Activities Sprint 3
Activities Sprint 4
Activities Sprint 5
Activities Sprint 6